# Mount Vernon Continuum of Care for the Homeless

## Meeting Minutes

## October 14, 2010

Meeting Facilitator: Yoav Spiegel

### Present:

| Jill Bradshaw-Soto, Legal Services of the Hudson Valley | T. Mastroeni, Mt. Vernon United Tenants |
| --- | --- |
| T. Brown, City of Mount Vernon | A. McDermott, City of Mounty Vernon |
| T. Garrett, Renaissance | R. Pennington, Westhab |
| J. Cooper, City of Mt. Vernon | Y. Spiegel, PD&D |
| C. Jones, City of Mt. Vernon | C. Sylvester, City of Mount Vernon |
| M. Mahoney, Legal Services of the Hudson Valley |  |

TOPICS:

# Welcomes and Introduction

# Announcements

- FY10 application – NOFA released – application due 11/18/10

- Project addresses needed for 2991 form. SSO and SRO projects are single site, addresses provided at meeting. Danielle will forward scattered site unit addresses to Yoav

- Renewal Exhibit 2 review

- Renewal Logic Model review – the FY09 versions of these two documents should be reviewed for errors/typos or changed contact information. Yoav will email these by this coming Monday, for return by next Friday.

- SF-424 and 2880 forms – Carmen and Yoav will handle these

- New project budget and Exhibit 2 – Carmen, Yoav, and Karl will draft the Exhibit 2. Yoav needs a line-item budget from Carmen as soon as possible.

- APR Update

Currently pending APRs, to be submitted through e-snaps:

Renaissance Chronic Homeless Outreach is due in two weeks (10/29). Draft of HMIS-generated APR has been provided for review, and is undergoing revision. e-snaps APR not yet created.

CMV Shallow Rent is due in two weeks (10/29). Draft of HMIS-generated APR has NOT been provided for review, and so is 1 month late.

Renaissance S+C (C60-4027) and CMV S+C V (C60-4030) are due for review on 10/25.

In addition, the APR for the extension period for S+C II C30-4025 is probably due in late December, and due for review in 1 month.

- Grant Fund drawdown report

See handout.

B70-4010 Shallow Rent has 4408 to be recouped. Request has already been sent to Lisa.

The two-year contract for Renaissance Chronic Homeless Outreach ended 7/31/10, but Renaissance has drawn less than half of the authorized funds; $40,951 remains. Renaissance must voucher for this money in next two weeks and have the funds drawn out of LOCCS, or it will be recouped by HUD and lost permanently.

CMV Shelter Plus Care projects are behind schedule and should have 1-3 beds added above contracted number of beds to catch up. These are S+C IV, S+C V, Renaissance S+C, and S+C for Vets, and YMCA S+C. This means CMV needs to find ~10 disabled homeless to place in these new beds, as has been discussed for months.

No clients yet identified for the empty C70-4026 S+C Vets. Most veterans seem to be housed elsewhere already.

FY09 grants (1-year renewals):

475B Shallow Rent, 485B MVUT Rehousing Assistance, 501B Mt. Vernon OWN, 621C CMV S+C II are all 7-8 months behind schedule and must be brought up to date ASAP!

- Other new business

Legal Services of Hudson Valley, Mount Vernon office:

- New intake hours are 9am to 12 noon. Clients can also do intake in the afternoon or on the phone by arrangement.

- LSHV has New York State member item funding to do Domestic Violence work in Mount Vernon. The funding also covers the attorneys to do social service benefits/ other family law/ special education/ and landlord-tenant work as well.

- Clients can call toll-free 1-877-574-8529, or call 914-813-6880, or walk-in to Mount Vernon office at 100 East 1st Street, 8th Floor

Next meeting November 10, 2010